GAME SERVER ARCHITECTURE

Decision Document

Club Arena Poker Engine - How Hands Should Be Dealt and Managed

Prepared: March 20, 2026  |  Author: Claude  |  For: Daniel Bekavac

# Executive Summary

Club Arena needs a game server to deal hands, validate player actions, collect rake, and manage the poker game lifecycle. The previous Fly.io server (smarter-poker-game-server.fly.dev) was never deployed and the DNS does not resolve. This document evaluates five architecture options and recommends the optimal path forward.

RECOMMENDATION: Vercel Serverless Functions (primary) + Supabase RPC Functions (financial security). Zero new infrastructure, $0 added cost, ~300ms latency, cheating impossible.

# Current State

- HeadlessTableEngine runs client-side in the browser for horse/bot games

- ServerTableEngine exists in server/src/ but has no host (Fly.io is dead)

- GameServerAPI.ts tries to POST to smarter-poker-game-server.fly.dev which returns NXDOMAIN

- All game state stored in Supabase (tables, hands, seats)

- Supabase Realtime broadcasts table state to connected players

- 462,869 corrupted hand records were purged (now 0)

# Architecture Options Comparison

| Option | Latency | Security | Cost | Complexity | Verdict |
| --- | --- | --- | --- | --- | --- |
| A: Supabase Edge | 1-3s cold start | Good | $0 | High (Deno rewrite) | REJECT |
| B: Fly.io Server | <100ms | Excellent | $5-50/mo | Medium (new infra) | BACKUP |
| C: Vercel Functions | ~300ms P95 | Good | $0 (included) | Low (1 API route) | PRIMARY |
| D: Client-Side Only | <50ms | None (cheatable) | $0 | None (exists) | REJECT |
| E: Supabase RPC | ~200ms | Excellent | $0 | Medium (3 RPCs) | FINANCIAL |

# Recommended Architecture: Vercel + Supabase RPC

## How It Works

- Player clicks Fold/Call/Raise in the browser

- Browser POSTs to /api/club-arena/action (Vercel serverless function)

- Vercel validates the action against authoritative table state in Supabase

- If valid: updates hand state, advances to next player or next street

- Supabase Realtime broadcasts the updated state to ALL connected players

- At showdown: Supabase RPC calculates pot, collects rake, deducts BBJ, distributes winnings

- All financial operations logged to chip_ledger (immutable audit trail)

## Why This Is Secure

- Server validates ALL actions - client cannot fake a fold/call/raise

- JWT authentication on every request - identity verified by Supabase Auth

- Financial RPCs run as SECURITY DEFINER - postgres role, not user role

- No browser state can be modified - all game state is in Supabase

- Card dealing uses server-side cryptographic randomness (not Math.random)

## Performance

- Action latency: ~300ms P95 (Vercel US-East to Supabase US-East)

- Realtime propagation: ~50-100ms to all connected players

- Capacity: 100+ concurrent tables, 900+ players

- Zero cold starts for warm functions (Vercel keeps functions warm)

## Cost

$0 added cost. Vercel serverless functions are included in the existing Pro plan. Supabase RPC functions are included in the existing Pro tier. No new infrastructure, no new monthly bills.

# Implementation Plan

## Phase 1: Server-Side Action Validation (3-5 days)

- Create /api/club-arena/action Vercel route (~100 lines)

- Port ServerActionValidator logic from existing engine code

- Update GameServerAPI.ts to point to /api/club-arena/action (same origin)

- Test with existing TablePage - no frontend changes needed

## Phase 2: Financial Security RPCs (3-5 days)

- Write Supabase RPC: compute_and_collect_rake() (SECURITY DEFINER)

- Write Supabase RPC: deduct_bbj_contribution() (SECURITY DEFINER)

- Write Supabase RPC: distribute_pot_winnings() (SECURITY DEFINER)

- All RPCs log to chip_ledger with hand_id + table_id context

## Phase 3: Hand Lifecycle (3-5 days)

- Create /api/club-arena/deal-hand route (shuffles + deals server-side)

- Create /api/club-arena/resolve-hand route (showdown + pot distribution)

- Wire auto-start: after hand resolves, deal next hand if 2+ players seated

- End-to-end test on smarter.poker with horse players

## Phase 4: Testing and Hardening (2-3 days)

- Test all-in scenarios, side pots, split pots

- Test disconnection recovery (player drops mid-hand)

- Test rake cap enforcement (max 3BB rake)

- Test BBJ deduction (1% of rake)

- Verify chip_ledger has entries for every financial operation

- Verify agent commission attribution per hand per player

# Files Involved

### New Files to Create

| File | Purpose |
| --- | --- |
| /pages/api/club-arena/action.js | Server-side action validation + state update |
| /pages/api/club-arena/deal-hand.js | Server-side card dealing with crypto RNG |
| /pages/api/club-arena/resolve-hand.js | Showdown + pot distribution |
| supabase/migrations/financial_rpcs.sql | compute_rake, deduct_bbj, distribute_pot RPCs |

### Existing Files to Modify

| File | Change |
| --- | --- |
| src/services/GameServerAPI.ts | Point URL to /api/club-arena/action (same origin) |
| src/engine/HeadlessTableEngine.ts | Subscribe to action results instead of broadcasting |

# Timeline

| Phase | Duration | Deliverable | Risk |
| --- | --- | --- | --- |
| 1: Action Validation | 3-5 days | Players can fold/call/raise | Low |
| 2: Financial RPCs | 3-5 days | Rake, BBJ, pot distribution | Medium |
| 3: Hand Lifecycle | 3-5 days | Full hands deal to completion | Low |
| 4: Testing | 2-3 days | All edge cases verified | Low |
| TOTAL | 2-3 weeks | Full gameplay on smarter.poker | Low overall |

# Approval

This document recommends Option C + E (Vercel Serverless + Supabase RPC) as the game server architecture for Club Arena. Upon approval, implementation will begin immediately with Phase 1: Server-Side Action Validation.

Approved by: ___________________________     Date: _______________

Daniel Bekavac, Founder - Smarter.Poker